## ActiveProjects
Project Health | Project Number | Department | Division | Project Name | Partner Project Cost | Maintenance Cost | Hosting Cost | Project Phase | Project Size | Business Model | Start Date | Target Date | Percentage of Project Complete | Effort | Duration (Work Days) | Product Manager | Project Sponsor | Executive Sponsor | SOW URL | Project Updated | Status Comments | Status | Project Health
Red | 001 | Department of Commerce and Consumer Affairs (DCCA) | Business Registration Division (BREG) | DCCA - BREG - Annuals Enhancements and Redesign | 0 | 0 | 0 | TEST | 3: Large | Self-funded | 2013-01-22 | 2016-06-23 | 90% | 2022 | 934 | Kristyne Tanaka | Ty Nohara | Ty Nohara | https://confluence.ehawaii.gov/download/attachments/28838102/DCCA-BREG-OnlineInitialFilingsForBusinessesPhase2%20SOW%2020011219.pdf?api=v2 | 2016-09-27 15:54 | Status Update - 9/27/16 - Berschneider, Teri 9/27/2016 3:54 PM HST Project is behind schedule due to competing project priorities and resource constraints. Partner is aware of project status and progress. HIC completed updates and bug fixes to business rules. Testing in progress. ------------------- | Open | Red
Green | 002 | Department of Business, Economic Development & Tourism (DBEDT) | Community-Based Economic Development Program (CBED) | DBEDT - BDSD - WP - Invest.hawaii.gov Support | 43374.29 | 0 | 1200 | MAINT | 1: Small | T&M | 2013-10-01 | 2016-12-31 | 75% | 670 | 762 | Lyle Fujikawa | Dennis T. Ling | Mary Alice Evans | https://confluence.ehawaii.gov/download/attachments/28838065/DBEDT-WebsiteHostingAndDesignServices-BDSDHosting%20SOW%20Addendum%2020130927.pdf?api=v2 | 2016-10-03 11:41 | General website updates completed this week - Warfield, Rosie 10/3/2016 11:41 AM HST General website updates completed this week, adding content and helping with newsletter sendout ------------------- | Open | Green
Green | 003 | Department of Labor and Industrial Relations (DLIR) | Workforce Development Division (WDD) | DLIR - WDD - WOTC eApplication | 60000 | 0 | 0 | TEST | 2: Medium | T&M | 2014-01-29 | 2016-11-28 | 95% | 713 | 379 | Mark Olds | Carol Kanayama | Elaine Young | https://confluence.ehawaii.gov/download/attachments/28838124/DLIR-WDD-WOTCeApplication%20SOW%20Amendment1%2020150514.pdf?api=v2 | 2016-09-26 10:04 | 2016OCT03 Status Update - Koehler, Jerome 10/3/2016 11:28 AM HST Prototype design for new workflow / landing page is currently still in development. ------------------- | Open | Green
Red | 004 | Department of Attorney General (AG) | Hawaii Criminal Justice Data Center (HCJDC) | AG - HCJDC - Sex Offender Information Management System (SOIMS) | 75000 | 0 | 0 | DEV | 2: Medium | T&M | 2014-03-31 | 2016-12-14 | 11% | 302 | 640 | Jennifer Sablan | Laureen Uwaine | Liane Moriyama | https://confluence.ehawaii.gov/download/attachments/28838062/AG-HCJDC-SexOffenderInformationManagementSystem%20SOW%20Amendment1%2020160308.pdf?api=v2 | 2016-09-27 15:04 | SOIMS - Shohet, Julie 9/27/2016 3:04 PM HST Met with Partner to review next steps ------------------- | Open | Red
Green | 005 | Office of Information Management and Technology (OIMT) | OIMT General | OIMT - WP - State Template Assistance | 50277.5 | 0 | 0 | DEV | 2: Medium | T&M | 2014-07-07 | 2016-12-31 | 78% | 666 | 574 | Bryce Fujii | Karen Higa | Keone Kali | https://confluence.ehawaii.gov/download/attachments/28838144/OIMT-WebsiteHostingInfrastructure%20SOW%2020140707.pdf?api=v2 | 2016-10-03 11:52 | Working on fixes to scroll template - Warfield, Rosie 10/3/2016 11:52 AM HST Working on fixes to scroll templateChristopher getting setup with access to Bryces dev enviro ------------------- | Open | Green
Red | 006 | Department of Land and Natural Resources (DLNR) | Division of Aquatic Resources (DAR) | DLNR - DAR - CMLS Fishing Report Modernization Phase 2 | 40000 | 0 | 0 | DEV | 2: Medium | T&M | 2014-08-01 | 2016-11-04 | 75% | 1137 | 555 | Reginal Kokubun | Frazer McGilvray |  | https://confluence.ehawaii.gov/download/attachments/28838126/DLNR-DAR-CMLSFunctionalityReporting%20SOW%20Amendment2%2020140722.pdf?api=v2 | 2016-09-14 14:09 | Cont. Improvements - Xu, Jing 9/15/2016 1:21 PM HST Continue to make improvement with the added PDF generation. ------------------- | Open | Red
Red | 007 | Department of Business, Economic Development & Tourism (DBEDT) | Foreign Trade Zone Division | DBEDT - FTZ9 - Bill Presentment | 0 | 0 | 0 | TEST | 0: Very Small | Self-funded | 2015-01-26 | 2016-10-31 | 88% | 47 | 435 | James Nakano | James Nakano | David Sikkink | https://confluence.ehawaii.gov/download/attachments/28838065/DBEDT-FTZ-BillPresentmentAndPaymentProcessing%20SOW%2020150127.pdf?api=v2 | 2016-09-14 14:09 | 2016.10.04 - Miyasato, Carrie 10/4/2016 8:19 AM HST no change ------------------- | Open | Red
Green | 008 | County of Kauai | Kauai Real Property | Kauai - RPT - RPT Redesign and Multiple Payments | 0 | 0 | 0 | DESIGN | 1: Small | Self-funded | 2015-03-09 | 2017-01-13 | 30% | 455 | 405 | Michelle Lizama | Michelle Lizama | Ken Shimonishi | https://confluence.ehawaii.gov/download/attachments/28838095/Kauai-Finance-OnlinePropertyTaxPayments%20SOW%20Amendment3%2020150415.pdf?api=v2 | 2016-10-04 13:29 | Project Update Week Ending 10/4/16 - Hsu, Amy 10/4/2016 1:30 PM HST Development delivered new UI in test successfully. Development continues with the Epic, Payments. ------------------- | Open | Green
Green | 009 | Department of Attorney General (AG) | Hawaii Criminal Justice Data Center (HCJDC) | AG - HCJDC - HIJIS Portal External Agency Access and ID Management | 18471 | 0 | 0 | LAUNCHED | 1: Small | T&M | 2015-08-18 | 2017-08-25 | 85% | 142 | 292 | Bryan Kushima | Clay Sato | Liane Moriyama | https://confluence.ehawaii.gov/download/attachments/28838062/AG-HCJDC-HIJISPortalDevelopmentAndSupportServices%20SOW%20Amendment2%2020151222.pdf?api=v2 | 2016-09-27 15:50 | 9/27/16 Status - Innotas, Reports 9/27/2016 3:49 PM HST HIC has deployed changes to production for the External ID Access on 9/21/16. Awaiting partner updates on their side to turn on the external access from HIJIS. ------------------- | Open | Green
Green | 011 | Department of Attorney General (AG) | Tax & Charities Division | AG - Tax & Charities - Charity Registration (Updates & Commercial Co Venturer) | 68036 | 0 | 0 | DEV | 2: Medium | T&M | 2015-10-13 | 2016-10-21 | 68% | 978 | 253 | Jodi Yi | Hugh Jones | Douglas Chin | https://confluence.ehawaii.gov/download/attachments/28838062/AG-TaxAndCharities-OnlineCharityRegistration%20SOW%20Amendment5%2020160201.pdf?api=v2 | 2016-10-04 13:17 | Project Update Week Ending 10/3/16 - Hsu, Amy 10/4/2016 1:18 PM HST Testing completed successfully. Pending production deployment approval by the partner. Sprint 13 continues. ------------------- | Open | Green
Green | 012 | Department of Land and Natural Resources (DLNR) | Hunter Education Program | DLNR - Hunter Ed - Online Course Registration System (Phase 3: Public) | 65000 | 0 | 0 | DEV |  | Hybrid | 2015-12-01 | 2017-01-30 | 40% | 1208 | 219 | Andrew Choy | Andrew Choy | Andrew Choy | https://confluence.ehawaii.gov/download/attachments/28838126/DLNR-HunterEd-HunterEducationAndRecordsMgmtSystem%20SOW%20Amendment3%2020160212.pdf?api=v2 | 2016-09-14 14:11 | 9/26 Status Update - Tran, Tony 9/26/2016 2:30 PM HST No change from last week Public Phase 3 - Iteration 2 - Sprint 1 DEV-in progress ------------------- | Open | Green
Green | 013 | Department of Land and Natural Resources (DLNR) | Bureau of Conveyances (BOC) | DLNR - BOC - LandLink 2016 Updates | 0 | 0 | 0 | MAINT | 2: Medium | Self-funded | 2016-01-01 | 2016-12-31 | 70% | 746 | 197 | Carol Ching, Hannah Domingo | Les Kobata | Nicki Thompson | https://confluence.ehawaii.gov/download/attachments/28838126/DLNR-BOC-BOCTitleAndRecordsManagementSystem_BACKEND%20SOW%2020100511.pdf?api=v2 | 2016-09-14 14:11 | Update - Bacungan, Laurenz 10/4/2016 3:48 PM HST No Update ------------------- | Open | Green
Green | 014 | Department of Labor and Industrial Relations (DLIR) | Hawaii Occupational Safety and Health Division (HIOSH) | DLIR - HIOSH - Inspection and Permitting (Maintenance) | 0 | 0 | 0 | MAINT | 3: Large | Free | 2016-01-04 | 2016-10-14 | 50% | 600 | 197 | Julius Dacanay | Norman Ahu | Linda Chu Takayama | https://confluence.ehawaii.gov/download/attachments/28838124/DLIR-HIOSH-Inspection%26PermitManagementSystem%20SOW%2020111208.pdf?api=v2 | 2016-09-26 14:29 | 10/3 Status Update - Tran, Tony 10/3/2016 2:30 PM HST Sprint 13 DEV complete - Partner reviewed it on 9/30. Pending Letter of Deployment signature to go to PROD w/ Sprint 13 this week Sprint 14 DEV in-progress ------------------- | Open | Green
Green | 015 | Department of Health (DOH) | Office of Health Status Monitoring (OHSM) | DOH - OHSM - Vital Records Ordering System: 2016 Maintenance | 0 | 0 | 0 | MAINT | 1: Small | Self-funded | 2016-01-04 | 2016-12-29 | 51% | 262 | 197 | Leatrice Tsubota | Alvin Onaka, PHD. | Keith Yamamoto | https://confluence.ehawaii.gov/download/attachments/28838114/DOH-OHSM-VitalRecordsOrdering%20SOW%2020020503.pdf?api=v2 | 2016-09-14 14:12 | 10/3 Status Update - Tran, Tony 10/3/2016 2:35 PM HST Had a Conference Call with REMATICS and Partner to Update the new API spec. Waiting on REMATICS to update API and next steps will be to update to the new API ------------------- | Open | Green
Green | 016 | Department of Accounting and General Services (DAGS) | State Procurement Office (SPO) | DAGS - SPO - Hawaii eProcurement System (HIePro) 2016 Updates | 0 | 0 | 0 | MAINT | 3: Large | Self-funded | 2016-01-04 | 2016-12-29 | 40% | 1850 | 197 | Bonnie Kahakui | Mara Smith | Sara Allen | https://confluence.ehawaii.gov/download/attachments/28838099/DAGS-SPO-HIePRO%20SOW%2020120411.pdf?api=v2 | 2016-09-14 14:13 | 10/3 Status Update - Tran, Tony 10/3/2016 2:23 PM HST September Sprint complete, Partner signed off for PROD update on 10/4 ------------------- | Open | Green
Green | 017 | Hawaii Teacher Standards Board (HTSB) | Hawaii Teacher Standards Board (HTSB) | HTSB - Licensing System 2016 Enhancements | 0 | 0 | 0 | MAINT |  | Self-funded | 2016-01-04 | 2016-12-30 | 65% | 434 | 197 | Lorrin Toma | Christina Simpson | Lynn Hammonds | https://confluence.ehawaii.gov/download/attachments/28838138/HTSB-OnlineLicensing%20SOW%2020090701.pdf?api=v2 | 2016-10-03 11:34 | 2016OCT03 Status Update - Koehler, Jerome 10/3/2016 11:35 AM HST Maintenance development continues. ------------------- | Open | Green
Green | 018 | Department of Health (DOH) | STD/AIDS Prevention Branch (SAPB) | DOH - SAPB - Medical Marijuana Registry 2016 Maintenance | 0 | 0 | 0 | MAINT |  | Self-funded | 2016-01-04 | 2016-12-30 | 74% | 506 | 197 | Scottina Ruis | Peter Whiticar | Peter Whiticar | https://confluence.ehawaii.gov/download/attachments/28838114/DOH-SAPB-MedicalMarijuanaRegistrationSystem%20SOW%2020140416.pdf?api=v2 | 2016-09-27 15:28 | MEDMJ - Shohet, Julie 9/27/2016 3:28 PM HST ongoing maintenance ------------------- | Open | Green
Red | 019 | Department of Land and Natural Resources (DLNR) | Division of Boating and Ocean Recreation (DOBOR) | DLNR - DOBOR - BARS Jan 2016 - June 2017 Maintenance | 0 | 99000 | 0 | MAINT |  | T&M | 2016-01-04 | 2017-06-30 | 0% | 89 | 197 | Kevin Yim | Kevin Yim | Ed Underwood | https://confluence.ehawaii.gov/download/attachments/28838126/DLNR-DOBOR-BARS%20SOW%20Amendment8%2020160727.pdf?api=v2 | 2016-10-03 11:29 | 2016OCT03 Status Update - Koehler, Jerome 10/3/2016 11:30 AM HST Requested meeting with DOBOR team (Jenna) to conduct training for the Vessel Management Tool. Awaiting response from Jenna. Aged report changes are currently being worked on. ------------------- | Open | Red
Green | 020 | Department of Business, Economic Development & Tourism (DBEDT) | Community-Based Economic Development Program (CBED) | DBEDT - CBED - Forms Application Enhancements 2016 | 10000 | 0 | 0 | SPEC |  | T&M | 2016-01-04 | 2017-06-30 | 40% | 0 | 197 | Marlene Hiraoka | Mark Ritchie | Richard Lim | https://confluence.ehawaii.gov/download/attachments/28838065/DBEDT-CBED-CBEDApplications%20SOW%20Addendum3%2020160122.pdf?api=v2 | 2016-09-14 14:14 | 2016.10.04 - Miyasato, Carrie 10/4/2016 8:16 AM HST no change ------------------- | Open | Green
Green | 022 | Department of Land and Natural Resources (DLNR) | Division of Forestry and Wildlife (DOFAW) | DLNR - DOFAW - Na Ala Hele Trails REWRITE (Phase II - Vendor) | 0 | 0 | 0 | DEV | 2: Medium | Self-funded | 2016-01-25 | 2016-12-05 | 97% | 1672 | 182 | Aaron Lowe | Aaron Lowe |  | https://confluence.ehawaii.gov/download/attachments/28838126/DLNR-DOFAW-NaAlaHeleTrailsAndAccessProgramRewrite%20SOW%2020150601.pdf?api=v2 | 2016-10-04 13:20 | Project Update Week Ending 10/4/16 - Hsu, Amy 10/4/2016 1:25 PM HST Project team met to review and discuss outstanding tasks. Development continues with bug fixes. ------------------- | Open | Green
Green | 023 | Department of Commerce and Consumer Affairs (DCCA) | Professional and Vocational Licensing Division (PVL) | DCCA - PVL - 2016 PVL Renewal Maintenance | 0 | 0 | 0 | MAINT | 1: Small | Self-funded | 2016-02-01 | 2016-10-28 | 85% | 0 | 177 | Charlene Oshiro | Celia Suzuki |  | https://confluence.ehawaii.gov/download/attachments/28838102/DCCA-PVL-OnlinePVLRenewals%20SOW%2020010312.pdf?api=v2 | 2016-09-14 14:15 | Prep for Oct Cycle - Xu, Jing 9/15/2016 1:19 PM HST Started the Oct Cycle prep work. On schedule. ------------------- | Open | Green
Red | 024 | Department of Attorney General (AG) | Tax & Charities Division | AG - Tax & Charities - Solicitor Registration 2016 Updates | 20973.81 | 0 | 0 | MAINT |  | T&M | 2016-02-22 | 2016-12-30 | 100% | 566 | 162 | Kathryn-Jean Kanemori | Kathryn-Jean Kanemori | Hugh Jones | https://confluence.ehawaii.gov/download/attachments/28838062/AG-TaxAndCharities-ProfessionalSolicitorRegistrationSystem%20SOW%20Amendment2%2020160201.pdf?api=v2 | 2016-09-14 14:15 | 2016.10.04 - Miyasato, Carrie 10/4/2016 8:15 AM HST Application in maintenance mode. ------------------- | Open | Red
Green | 025 | Hawaii State Public Library System (HSPLS) | Hawaii State Public Library System | HSPLS - WP - hawaiilibraries.org | 45760 | 0 | 0 | DEV | 2: Medium | T&M | 2016-03-21 | 2016-10-06 | 94% | 1123 | 142 | Stacey Aldrich | Stacey Aldrich |  | https://confluence.ehawaii.gov/download/attachments/28838054/LibrarySOW20160404.pdf?version=1&modificationDate=1459901222626&api=v2 | 2016-10-03 11:47 | Final go live prep for Oct 6 - Warfield, Rosie 10/3/2016 11:48 AM HST Completing site updates, getting site on latest version of WP Clean up of all events and making sure consistentTesting ------------------- | Open | Green
Green | 026 | Department of Labor and Industrial Relations (DLIR) | Hawaii Occupational Safety and Health Division (HIOSH) | DLIR - HIOSH - Collections | 0 | 0 | 0 | TEST | 0: Very Small | Self-funded | 2016-04-01 |  | 95% | 180 | 133 | Bert Yorita | Norman Ahu | Linda Chu Takayama | https://confluence.ehawaii.gov/download/attachments/28838124/DLIR-HIOSH-Collections%20SOW%2020160401.pdf?api=v2 | 2016-09-14 14:15 | 9/26/2016 - Ramos, Burt 9/27/2016 3:55 PM HST Partner meeting on Friday 9/30 to go over next steps ------------------- | Open | Green
Red | 027 | Department of Land and Natural Resources (DLNR) | Division of Forestry and Wildlife (DOFAW) | DLNR - DOFAW - Hunt Lottery Drawing System | 5000 | 0 | 0 | SPEC |  | T&M | 2016-04-28 | 2016-08-22 | 0% | 93 | 114 | Shane De Mattos | Jim Cogswell | David Smith | https://confluence.ehawaii.gov/download/attachments/28838126/DLNR-DOFAW-HuntLotteryDrawingSystem%20SOW%2020160428.pdf?api=v2 | 2016-09-14 14:16 | 9/9/16 update - Innotas, Reports 9/9/2016 8:41 AM HST Project behind schedule. Spec document review and updates in progress. ------------------- | Open | Red
Red | 028 | Department of Budget and Finance (B&F) | Employer Union Health Benefits Trust Fund (EUTF) | B&F - EUTF - Payment Processing | 0 | 0 | 0 | DEV | 0: Very Small | Self-funded | 2016-05-11 | 2016-10-07 | 85% | 16 | 105 | Donna Tonaki | Donna Tonaki | Donna Tonaki | https://confluence.ehawaii.gov/download/attachments/28838111/B%26F-EUTF-ParticipantPaymentProcessing%20SOW%2020160420.pdf?api=v2 | 2016-09-14 14:16 | 9/27/2016 - Ramos, Burt 9/27/2016 3:57 PM HST Waiting on these items: 1. Signed Letter of Deployment for Restricted Release 12. Login and passwords to Axway folders ------------------- | Open | Red
Green | 030 | Judiciary (JUD) | JUD General | Judiciary - eBench Warrants Circuit and Family Court Addition | 0 | 0 | 0 | TEST |  | Free | 2016-05-31 | 2017-01-12 | 90% | 69 | 91 | Dana Nakasato | Calvin Ching | Kevin Thornton | https://confluence.ehawaii.gov/download/attachments/28838140/Judiciary-OnlineTrafficWarrants%20SOW%2020070815.pdf?api=v2 | 2016-09-14 14:16 | NO NEW UPDATE UNTIL JAN 2017 - Pick, Janet 9/22/2016 8:53 AM HST On track: Testing complete - no additional work needed until launch. Awaiting green light from Judiciary to go live in Jan 2017 when their JIMS system is updated with Circuit and Family Court warrants. ------------------- | Open | Green
Yellow | 031 | County of Kauai | Kauai Police Department (KPD) | Kauai - KPD - eBW Web Service | 0 | 0 | 0 | SPEC | 0: Very Small | T&M | 2016-06-13 | 2016-11-07 | 10% | 0 | 82 | Stacy Perreira | Rob Gausepohl |  | https://confluence.ehawaii.gov/download/attachments/28838095/Kauai-KPD-eBenchWarrantsInterface%20SOW%2020160613.pdf?api=v2 | 2016-09-22 08:52 | 9/27/16 Status - Innotas, Reports 9/27/2016 3:56 PM HST On track. Sending partner sample output from web service this week. ------------------- | Open | Yellow
Green | 032 | County of Hawaii | Hawaii County Police Department (HCPD) | Hawaii - HCPD - eBW Web Service | 0 | 0 | 0 | SPEC | 0: Very Small | T&M | 2016-06-27 |  | 0% | 0 | 72 | Scott Uehara | Dana Nakasato | Kevin Thornton | https://confluence.ehawaii.gov/download/attachments/28838086/Hawaii-HCPD-eBenchWarrantsInterface%20SOW%2020160627.pdf?api=v2 | 2016-09-14 14:17 | 9/27/16 Status - Innotas, Reports 9/27/2016 3:55 PM HST On track. Sending partner sample output from web service this week. ------------------- | Open | Green
Green | 033 | Hawaii State Legislature | Senate | Legislature - Senate - Annual / SR54 Report | 0 | 0 | 0 | DEV | 2: Medium | Free | 2016-07-04 | 2016-12-20 | 70% | 246 | 67 | Russell Castagnaro | Russell Castagnaro | Russell Castagnaro | N/A | 2016-09-26 09:08 | 2016SEP26 Status Update - Koehler, Jerome 9/26/2016 9:08 AM HST Information gathering is behind schedule. First week of narratives creation has begun. ------------------- | Open | Green
Green | 034 | Honolulu City Council | Office of the City Clerk (OCC) | Honolulu City Council - City Clerk - Online Absentee Ballots 2016 General | 0 | 0 | 0 | TEST | 1: Small | Free | 2016-07-26 | 2016-11-08 | 65% | 24 | 52 | Rex Quidilla | Chadd Kadota | Glen Takahashi | https://confluence.ehawaii.gov/download/attachments/28838136/HCC-CityClerk-AbsenteeVoterBallets%20SOW%2020140515.pdf?api=v2 | 2016-09-27 15:23 | HNLVOTE - Shohet, Julie 9/27/2016 3:23 PM HST Communications ------------------- | Open | Green
Red | 035 | Department of Land and Natural Resources (DLNR) | Bureau of Conveyances (BOC) | DLNR - BOC - Doc Search Updates (Phase 1) | 0 | 0 | 0 | DESIGN |  | Self-funded | 2016-08-08 | 2016-08-26 | 0% | 19 | 43 | Carol Ching, Hannah Domingo | Les Kobata | Les Kobata | https://confluence.ehawaii.gov/download/attachments/28838126/DLNR-BOC-OnlinePaymentProcessingForConveyancesRecords_DocSearch%20SOW%20Amendment1%2020160728.pdf?api=v2 | 2016-09-14 14:18 | Update - Bacungan, Laurenz 10/4/2016 3:48 PM HST Assigned Sprint 1 to developer. ------------------- | Open | Red
Red | 036 | City and County of Honolulu | Department of Liquor Control | Hawaii - Liquor Control - Licensing & Permitting Application | 0 | 0 | 0 | DEV |  | Self-funded | 2016-08-08 | 2016-10-17 | 0% | 42 | 43 | Marcia Matsui | Marcia Matsui | Gerald Takase | https://confluence.ehawaii.gov/download/attachments/28838086/Hawaii-LiquorControl-LicensingAndPermittingApp%20SOW%2020160808.pdf?api=v2 | 2016-10-03 11:56 | 2016OCT03 Status Update - Koehler, Jerome 10/3/2016 11:57 AM HST Prototype Deployed to TEST. Next Step: Set up meeting with internal team. ------------------- | Open | Red
Green | 037 | County of Hawaii | Mass Transit Agency | Hawaii - Mass Transit - HeleOn Mobile Bus App | 0 | 0 | 0 | DEV |  | T&M | 2016-08-08 | 2016-11-09 | 20% | 13 | 43 | Tiffany Kai | Tiffany Kai | Mayor Kenoi | https://confluence.ehawaii.gov/download/attachments/28838086/Hawaii-MassTransitAgency-MobileBusApplication%20SOW%2020160808.pdf?api=v2 | 2016-09-27 16:20 | 2016.10.04 - Miyasato, Carrie 10/4/2016 8:21 AM HST On track. Development in progrsss. ------------------- | Open | Green
Green | 038 | Department of Accounting and General Services (DAGS) | State Procurement Office (SPO) | DAGS - SPO - Hawaii Awards and Notices Data System (HANDS) | 0 | 0 | 0 | SPEC |  | T&M | 2016-08-15 | 2017-11-14 | 0% | 0 | 38 |  |  |  | https://confluence.ehawaii.gov/download/attachments/28838099/DAGS-SPO-HawaiiAwardsAndNoticesDataSystem%20SOW%2020160816.pdf?api=v2 | 2016-09-14 14:18 | 10/3 status Update - Tran, Tony 10/3/2016 2:18 PM HST Regroup with Designer this week to create mock-upRegroup with Partner to grab the PANS DB ------------------- | Open | Green