## PPM Dashboard - All Projects
HIC Project Dashboard - February 20, 2017
Project Name | Partner Project Cost | Partner Maintenance Cost | Partner Hosting Cost | Status | Phase | Business Model | Start Date | Target Date | Project Complete % | Effort (Hours) | Product Manager | Project Sponsor | Executive Sponsor | Project Health
AG - HCJDC - Covered Offender (OFFENDER) - API Update |  |  |  | 1: Open | MAINT | Free | 2016-11-18 | 2017-04-28 | 88% | 87.25 | Jennifer Bishop |  |  | On Track
AG - HCJDC - Sex Offender Information Management System (SOIMS) | 19837.69 |  |  | 1: Open | DEV | T&M | 2014-03-31 | TBD | 20% | 124 | Jennifer Sablan | Laureen Uwaine | Liane Moriyama | On Track
AG - Tax & Charities - Charity Registration (Updates & Commercial Co Venturer) | 42730.35 |  |  | 1: Open | DEV | T&M | 2015-09-28 | 2017-04-10 | 74% | 1779.1 | Jodi Yi | Hugh Jones | Douglas Chin | On Track
AG - Tax & Charities - Solicitor Registration 2016/2017 Updates | 20973.81 |  |  | 1: Open | MAINT | T&M | 2016-02-22 | 2017-03-10 | 98% | 850.75 | Kathryn-Jean Kanemori | Kathryn-Jean Kanemori | Hugh Jones | On Track
DAGS - SPO - Hawaii Awards and Notices Data System (HANDS) | 0 |  |  | 1: Open | DEV | T&M | 2016-08-15 | 2018-02-01 | 15% | 594 |  |  |  | On Track
DAGS - SPO - Hawaii eProcurement System (HIePro) 2017 Updates | 0 |  |  | 1: Open | MAINT | Self-funded | 2017-01-02 | 2017-12-31 | 12% | 146 | Bonnie Kahakui | Mara Smith | Sarah Allen | On Track
DBEDT - BDSD - WP - Invest.hawaii.gov Support 2017 |  |  |  | 1: Open | MAINT | T&M | 2017-01-02 | 2017-12-31 | 11% | 104 | Lyle Fujikawa | Dennis T. Ling | Mary Alice Evans | On Track
DBEDT - CBED - Forms Application Enhancements 2016/2017 | 10000 |  |  | 1: Open | SPEC | T&M | 2016-01-04 | 2017-06-30 | 40% | 0 | Marlene Hiraoka | Mark Ritchie | Richard Lim | On Track
DBEDT - Energy - Solar Water Heater Variance | 15706.8 |  |  | 1: Open | TEST | Hybrid | 2015-09-14 | 2016-12-06 | 86% | 224 | Dean Masai | Dean Masai | Mark Glick | At Risk
DBEDT - FTZ9 - Bill Presentment | 0 |  |  | 1: Open | TEST | Self-funded | 2015-01-26 | 2016-10-31 | 88% | 47 | James Nakano | James Nakano | David Sikkink | Behind
DLIR - HIOSH - Collections | 0 |  |  | 1: Open | TEST | Self-funded | 2016-04-01 |  | 96% | 323 | Bert Yorita | Norman Ahu | Linda Chu Takayama | On Track
DLIR - HIOSH - Inspection and Permitting (Enhancements) - 2017 | 0 |  |  | 1: Open | MAINT | Self-funded | 2016-12-23 | 2017-12-31 | 40% | 70.5 | Julius Dacanay | Norman Ahu | Linda Chu Takayama | On Track
DLIR - WDD - WOTC eApplication | 60000 |  |  | 1: Open | TEST | T&M | 2014-01-29 | 2016-11-28 | 95% | 774 | Mark Olds | Carol Kanayama | Elaine Young
DLNR - BOC - Doc Search Updates (Phase 1) | 0 |  |  | 1: Open | DESIGN | Self-funded | 2016-08-08 | 2016-08-26 | 0% | 19 | Carol Ching, Hannah Domingo | Les Kobata | Les Kobata | Behind
DLNR - DOBOR - BARS Jan 2016 - June 2017 Maintenance | 0 |  |  | 1: Open | MAINT | T&M | 2016-01-04 | 2017-06-30 | 55% | 110 | Kevin Yim | Kevin Yim | Ed Underwood | On Track
DLNR - DOFAW - Hunt Lottery Drawing System | 5000 |  |  | 1: Open | SPEC | T&M | 2016-04-28 | 2017-08-22 | 0% | 289 | Shane De Mattos | Jim Cogswell | David Smith | Behind
DLNR - DOFAW - Na Ala Hele Trails REWRITE (Phase II - Vendor) | 0 |  |  | 1: Open | TEST | Self-funded | 2016-01-25 | 2017-03-29 | 99% | 1849 | Aaron Lowe | Aaron Lowe |  | On Track
DLNR - Hunter Ed - Online Course Registration System (Phase 3: Public) | 65000 |  |  | 1: Open | DEV | Hybrid | 2015-12-01 | 2017-06-01 | 95% | 2165 | Andrew Choy | Andrew Choy | Andrew Choy | On Track
DOH - ADAD - Clean and Sober Home Registry | 0 |  |  | 1: Open | SPEC | T&M | 2016-03-30 | 2017-07-03 | 10% | 128 | Bolan, Angela | Mersereau, Eddie |  | On Track
DOH - OHSM - Vital Records Ordering System: 2017 Maintenance | 0 |  |  | 1: Open | MAINT | Self-funded | 2016-01-04 | 2017-12-31 | 95% | 485 | Leatrice Tsubota | Alvin Onaka, PHD. | Keith Yamamoto | On Track
DOH - SAPB - Medical Marijuana Registry 2017 Maintenance | 0 |  |  | 1: Open | MAINT | Self-funded | 2017-01-02 | 2017-12-29 | 15% | 368.5 | Scottina Ruis | Peter Whiticar | Peter Whiticar | On Track
DOH - TBB - Client Registry Enhancements 2017 | 0 |  |  | 1: Open | MAINT | Free | 2017-01-30 | 2017-06-30 | 0% | 4.75 | Trudy Murakami | Richard Brostrom |  | On Track
ETS - WP - State Template Assistance 2017 |  |  |  | 1: Open | DEV | T&M | 2017-01-02 | 2017-12-31 | 10% | 70 | Bryce Fujii | Bryce Fujii |  | On Track
Hawaii - HCPD - eBW Web Service | 0 |  |  | 1: Open | TEST | T&M | 2016-06-27 | 2017-04-28 | 75% | 21 | Scott Uehara |  |  | On Track
Hawaii - Liquor Control - Licensing & Permitting Application | 0 |  |  | 1: Open | DEV | Self-funded | 2016-08-08 | 2017-04-03 | 40% | 215 | Marcia Matsui | Marcia Matsui | Gerald Takase | At Risk
Hawaii - Parks & Rec - Mauna Kea Recreation Permits - Groups |  |  |  | 1: Open | TEST | Self-funded | 2016-12-01 | 2017-03-01 | 98% | 110 | Grant Nagata | Reid Sewake | Clayton Honma | On Track
HSPLS - WP - librarieshawaii.org - Phase 2 | 2957 |  |  | 1: Open | DEV | T&M | 2016-11-01 | 2017-12-31 | 15% | 84 | Stacey Aldrich | Stacey Aldrich |  | On Track
JUD - Mobile App | 10451 |  |  | 1: Open | LAUNCHED | T&M | 2016-10-14 | 2017-01-17 | 95% | 205 | Deborah Murray | Deborah Murray | Rod Maile | On Track
Judiciary - Policy and Planning - Appellate Court Judge Evaluation 2017 February | 0 |  |  | 1: Open | TEST | Free | 2016-12-22 | 2017-03-31 | 50% | 5 | Michael Oki |  |  | On Track
Kauai - KPD - eBW Web Service | 0 |  |  | 1: Open | TEST | T&M | 2016-06-13 | 2017-04-28 | 75% | 23.25 | Stacy Perreira | Rob Gausepohl |  | On Track
Kauai - RPT - RPT Redesign Phase I (Multiple Payments) | 0 |  |  | 1: Open | TEST | Self-funded | 2015-03-09 | 2017-02-28 | 95% | 188 | Michelle Lizama | Michelle Lizama | Ken Shimonishi | On Track
Kauai - RPT - RPT Redesign Phase II (Notifications) | 0 |  |  | 1: Open | DEV | Self-funded | 2017-01-30 | 2017-05-31 | 3% | 7 | Michelle Lizama | Michelle Lizama | Ken Shimonishi | On Track
CCHNL - DCS - Grants Document Management System |  |  |  | 2: Proposed - SOW | SOW | T&M |  |  | 0% | 0 | Gabriel Naeole | Barbara Yamashita | Gary Nakata
DCCA - INS - Licensee Self-Service |  |  |  | 2: Proposed - SOW | SOW | Free |  |  | 0% |  | Ai Chen Rakieten | Gordon Ito
DLNR - DOFAW - ePermitting - Gate Combination |  |  |  | 2: Proposed - SOW | SOW | T&M |  |  | 0% | 2 | Aaron Lowe | Marigold Zoll | David Smith
DLNR - DOFAW - State Tree Nursery Seedling Orders |  |  |  | 2: Proposed - SOW | SOW | Self-funded | 2016-11-07 | 2017-05-05 | 0% |  | Jacob Witcraft | Jay Hatayama
DOD - WP - dod.hawaii.gov/ohs |  |  |  | 2: Proposed - SOW | SOW | T&M |  |  | 0% | 29
DOH - OHCA - Medical Marijuana Dispensary & Patient Registry Systems Inteface |  |  |  | 2: Proposed - SOW | SOW | T&M |  |  | 0% |  | Peggy Leuong | Keith Reidley
DOH - OHSM - Hawaii Violent Death Reporting System |  |  |  | 2: Proposed - SOW | SOW | T&M |  |  | 0% |  | Brian Pang | Alvin Onaka
DOH - SAPB - Medical Marijuana Registry 2017 Enhancements |  |  |  | 2: Proposed - SOW | SOW | T&M |  |  | 0% | 27 | Scottina Ruis | Peter Whiticar | Peter Whiticar
DOH - SCMH - State Council on Mental Health Website |  |  |  | 2: Proposed - SOW | SOW | T&M | 2016-11-01 | 2017-03-07 | 0% | 30
DPS - NED - Online Registration Renewal Fee Amendment |  |  |  | 2: Proposed - SOW | SOW | Self-funded |  |  | 0% |  | Drina Labasan | David Thornton
Hawaii - Parks & Rec - Mauna Kea Recreation Permits - Tour Operators |  |  |  | 2: Proposed - SOW | SOW | Self-funded | 2016-12-01 |  | 80% | 0 | Grant Nagata | Reid Sewake | Clayton Honma
JUD - TVB - Online Driver History & Abstract |  |  |  | 2: Proposed - SOW | SOW | Self-funded |  |  | 0% |  | Korin Okada | Kevin Thornton | Rodney Maile
UH - TIM - www.tim.hawaii.edu |  |  |  | 2: Proposed - SOW | SOW | T&M | 2016-09-14 | 2017-05-31 | 0% | 35 | Alan S Okimoto | Thomas Bingham
B&F - EUTF - Beneficiary Reimbursement |  |  |  | 3: Proposed - INIT | INIT | Unknown |  |  | 0% |  |  | Raymond Kan | Rodney Shinno
B&F - EUTF - Online Certification |  |  |  | 3: Proposed - INIT | INIT | Unknown |  |  | 0% |  |  | Raymond Kan | Rodney Shinno
CCHNL - DCS - DMV / State ID |  |  |  | 3: Proposed - INIT | INIT | Self-funded |  |  | 0% | 0
CCHNL - DCS - Taxicab Licensing |  |  |  | 3: Proposed - INIT | INIT | Unknown |  |  | 0% |  |  |  | Galen Inouye
DCCA - PVL - Continuing Education System |  |  |  | 3: Proposed - INIT | INIT | Unknown |  | 2017-04-01 | 0% |  | Charlene Oshiro | Celia Suzuki
DCCA - RICO - Consolidated Report for Licensees |  |  |  | 3: Proposed - INIT | INIT | Unknown |  |  | 0% |  |  | Daria Loy-Goto
DCCA - RICO - Contractor TIP Submission |  |  |  | 3: Proposed - INIT | INIT | Unknown |  |  | 0% |  |  | Daria Loy-Goto
DCCA - RICO - Online Settlement Agreement Payment |  |  |  | 3: Proposed - INIT | INIT | Unknown |  |  | 0% |  |  | Daria Loy-Goto
DOH - ADAD - Certified Substance Abuse Counselor Application & Registry System |  |  |  | 3: Proposed - INIT | INIT | T&M |  |  | 0% |  | Angela Bolan | Edward Mersereau
DOH - ADAD - Certified Substance Abuse Counselor Public Search |  |  |  | 3: Proposed - INIT | INIT | T&M |  |  | 0% |  | Angela Bolan | Edward Mersereau
JUD - General - Forfeited Bonds |  |  |  | 3: Proposed - INIT | INIT | Unknown |  |  | 0%
Kauai - Real Property Tax – Bill Presentment |  |  |  | 3: Proposed - INIT | INIT | Unknown |  |  | 0%
Kauai - RPT - SOW Amendment 4 |  |  |  | 3: Proposed - INIT | INIT | Unknown | 2017-01-27
AG - Tax & Charities - Charity Registration (Invoicing System) | 0 |  |  | 4: Hold | SPEC | Hybrid |  |  | 0% | 0 | Kathryn-Jean Kanemori | Kathryn-Jean Kanemore | Hugh Jones | On Track
DLNR - Hunter Ed - WP - Instructor Resource Site | 0 |  |  | 4: Hold | SPEC | T&M | 2016-10-10 | 2017-07-10 | 0% | 0 |  | Andrew Choy | Andrew Choy | On Track
Judiciary - eBench Warrants Circuit and Family Court Addition | 0 |  |  | 5: Completed | LAUNCHED | Free | 2016-05-31 | 2017-01-23 | 100% | 111 | Dana Nakasato | Calvin Ching | Kevin Thornton | On Track
CCHNL - DCS - DMV Site | 0 |  |  | 6: Canceled | SOW | T&M |  |  | 0% | 0
Hawaii - Mass Transit - HeleOn Mobile Bus App (Phase 1) | 0 |  |  | 6: Canceled | TEST | T&M | 2016-08-08 | 2016-11-14 | 85% | 427 | Tiffany Kai | Tiffany Kai | Mayor Kenoi | Behind
UH - IFA - Mauna Kea Parking | 0 |  |  | 6: Canceled | INIT | T&M |  |  |  | 1 | Stewart Hunter