## PPM Dashboard - All Projects
HIC Project Dashboard - May 23, 2017
Project Name | Partner Project Cost | Partner Maintenance Cost | Partner Hosting Cost | Status | Phase | Business Model | Start Date | Target Date | Project Complete % | Effort (Hours) | Partner Project Manager | Partner Project Sponsor | Partner Executive Sponsor | Project Health
AG - HCJDC - Covered Offender (OFFENDER) - API Update |  |  |  | 1: Open | MAINT | Free | 2016-11-18 | 2017-06-30 | 88% | 115.5 | Jennifer Bishop | Laureen Uwaine | Liane Moriyama | On Track
AG - HCJDC - Sex Offender Information Management System (SOIMS) | 19837.69 | 0 | 0 | 1: Open | DEV | T&M | 2014-03-31 | TBD | 25% | 193 | Jennifer Sablan | Laureen Uwaine | Liane Moriyama | On Track
AG - Tax & Charities - Charity Registration (Amendment 5 updates) | 42730.35 |  | 0 | 1: Open | DEV | T&M | 2015-09-28 | 2017-09-30 | 74% | 2491.87 | Jodi Yi | Hugh Jones | Douglas Chin | On Track
AG - Tax & Charities - Solicitor Registration 2016/2017 Updates | 20973.81 | 0 | 0 | 1: Open | MAINT | T&M | 2016-02-22 | 2017-08-31 | 75% | 981.93 | Kathryn-Jean Kanemori | Kathryn-Jean Kanemori | Hugh Jones | On Track
DAGS - SPO - Hawaii Awards and Notices Data System (HANDS) | 0 | 0 | 0 | 1: Open | DEV | T&M | 2016-08-15 | 2018-02-01 | 50% | 862 | Bonnie Kahakui | Mara Smith | Sarah Allen | On Track
DAGS - SPO - Hawaii eProcurement System (HIePro) 2017 Updates | 0 | 0 | 0 | 1: Open | MAINT | Self-funded | 2017-01-02 | 2017-12-31 | 65% | 735 | Bonnie Kahakui | Mara Smith | Sarah Allen | On Track
DBEDT - BDSD - WP - Invest.hawaii.gov Support 2017 | 13340.87 | 0 | 1200 | 1: Open | MAINT | T&M | 2017-01-02 | 2017-12-31 | 35% | 225 | Lyle Fujikawa | Dennis T. Ling | Mary Alice Evans | On Track
DBEDT - CBED - Forms Application Enhancements 2016/2017 | 10000 | 0 | 0 | 1: Open | SPEC | T&M | 2016-01-04 | 2017-06-30 | 80% | 117 | Marlene Hiraoka | Mark Ritchie | Richard Lim | On Track
DBEDT - FTZ9 - Bill Presentment | 0 | 0 | 0 | 1: Open | TEST | Self-funded | 2015-01-26 |  | 88% | 47 | James Nakano | James Nakano | David Sikkink | At Risk
DLIR - HIOSH - Collections | 0 | 0 | 0 | 1: Open | TEST | Self-funded | 2016-04-01 |  | 96% | 353 | Bert Yorita | Norman Ahu | Linda Chu Takayama | On Track
DLIR - HIOSH - Inspection and Permitting (Enhancements) - 2017 | 0 | 0 | 0 | 1: Open | MAINT | Self-funded | 2016-12-23 | 2017-12-31 | 75% | 142 | Julius Dacanay | Norman Ahu | Linda Chu Takayama | On Track
DLIR - WDD - WOTC eApplication | 60000 | 0 | 0 | 1: Open | TEST | T&M | 2015-05-15 | 2017-06-30 | 70% | 1240 | Mark Olds | Carol Kanayama | Elaine Young | At Risk
DLNR - BOC - Doc Search Updates (Phase 1) | 0 | 0 | 0 | 1: Open | DESIGN | Self-funded | 2016-08-08 | 2017-06-12 | 0% | 19 | Carol Ching, Hannah Domingo | Les Kobata | Les Kobata | On Track
DLNR - DOBOR - BARS Jan 2016 - June 2017 Maintenance | 0 | 99000 | 0 | 1: Open | MAINT | T&M | 2016-01-04 | 2017-06-30 | 55% | 110 | Kevin Yim | Kevin Yim | Ed Underwood | On Track
DLNR - DOFAW - ePermitting - Trails Day Use Permitting System |  |  |  | 1: Open | MAINT | Self-funded |  |  |  |  | Aaron Lowe | Marigold Zoll | David Smith | On Track
DLNR - DOFAW - Hunt Lottery Drawing System | 5000 | 0 | 0 | 1: Open | SPEC | T&M | 2016-04-28 | 2017-08-22 | 0% | 289 | Shane De Mattos | Jim Cogswell | David Smith | On Track
DLNR - DOFAW - Na Ala Hele Trails REWRITE (Phase II - Vendor) | 0 | 0 | 0 | 1: Open | TEST | Self-funded | 2016-01-25 | 2017-05-29 | 99% | 1849 | Aaron Lowe | Aaron Lowe |  | Behind
DLNR - Hunter Ed - Online Course Registration System (Phase 3: Public) | 65000 | 0 | 0 | 1: Open | DEV | Hybrid | 2015-12-01 | 2017-08-01 | 95% | 2332 | Andrew Choy | Andrew Choy | Andrew Choy | On Track
DOH - ADAD - Clean and Sober Home Registry | 0 | 0 | 0 | 1: Open | SPEC | T&M | 2016-03-30 | 2017-07-03 | 50% | 417.857 | Bolan, Angela | Mersereau, Eddie |  | On Track
DOH - OHCA - Medical Marijuana Dispensary & Patient Registry Systems Inteface |  |  |  | 1: Open | TEST | T&M | 2017-03-06 |  | 60% | 91 | Peggy Leong | Keith Ridley |  | On Track
DOH - OHSM - Vital Records Ordering System: 2017 Maintenance | 0 | 0 | 0 | 1: Open | MAINT | Self-funded | 2017-01-02 | 2017-12-31 | 95% | 505 | Leatrice Tsubota | Alvin Onaka, PHD. | Keith Yamamoto | On Track
DOH - SAPB - Medical Marijuana Registry 2017 Enhancements |  |  |  | 1: Open | SPEC | T&M |  |  | 0% | 35 | Scottina Ruis | Peter Whiticar | Peter Whiticar | Behind
DOH - SAPB - Medical Marijuana Registry 2017 Maintenance | 0 | 0 | 0 | 1: Open | MAINT | Self-funded | 2017-01-02 | 2017-12-29 | 40% | 1043.38 | Scottina Ruis | Peter Whiticar | Peter Whiticar | On Track
DOH - TBB - Client Registry Enhancements 2017 | 0 | 0 | 0 | 1: Open | MAINT | Free | 2017-01-30 | 2017-06-30 | 100% | 105 | Trudy Murakami | Richard Brostrom |  | On Track
ETS - WP - State Template Assistance 2017 | 7463.43 | 0 | 0 | 1: Open | DEV | T&M | 2017-01-02 | 2017-12-31 | 25% | 92 | Bryce Fujii | Bryce Fujii |  | On Track
Hawaii - Liquor Control - Licensing & Permitting Application | 0 | 0 | 0 | 1: Open | DEV | Self-funded | 2016-08-08 | 2017-06-13 | 95% | 654 | Marcia Matsui | Marcia Matsui | Gerald Takase | Behind
Hawaii - Parks & Rec - Mauna Kea Recreation Permits - Groups |  |  |  | 1: Open | TEST | Self-funded | 2016-12-01 | 2017-06-08 | 94% | 309 | Grant Nagata | Reid Sewake | Clayton Honma | Behind
HSPLS - WP - librarieshawaii.org - Phase 2 | 9142.09 |  | 1200 | 1: Open | MAINT | T&M | 2016-11-01 | 2017-12-31 | 40% | 170 | Stacey Aldrich | Stacey Aldrich |  | On Track
Judiciary - Policy and Planning - Family Court Judge Evaluation 2017 April | 0 | 0 | 0 | 1: Open | TEST | Free | 2017-04-11 |  | 90% | 9 | Michael Oki |  |  | On Track
Kauai - RPT - RPT Redesign Phase II (Notifications) | 0 | 0 | 0 | 1: Open | DEV | Self-funded | 2017-01-30 | 2017-06-14 | 80% | 103 | Michelle Lizama | Michelle Lizama | Ken Shimonishi | On Track
DOH - ADAD - Public Inspection & Complaints Portal |  |  |  | 2: Proposed - SOW | SOW | T&M |  |  |  |  | Angela Bolan | Edward Mersereau
DOH - SCMH - State Council on Mental Health Website |  |  |  | 2: Proposed - SOW | SOW | T&M | 2016-11-01 | 2017-03-07 | 0% | 31
DLNR - DOFAW - ePermitting - Gate Combination |  |  |  | 2: Proposed - SOW | INIT | T&M | TBD | TBD | 0% | 2 | Aaron Lowe | Marigold Zoll | David Smith
DOD - WP - dod.hawaii.gov/ohs |  |  |  | 2: Proposed - SOW | SOW | T&M |  |  | 0% | 29
DCCA - INS - Licensee Self-Service |  |  |  | 2: Proposed - SOW | SOW | Free |  |  | 0% |  | Ai Chen Rakieten | Gordon Ito
DPS - NED - Online Registration Renewal Fee Amendment |  |  |  | 2: Proposed - SOW | SOW | Self-funded |  |  | 0% |  | Drina Labasan | David Thornton
Kauai - RPT - SOW Amendment 4 |  |  |  | 2: Proposed - SOW | SOW | Unknown | 2017-01-27 |  |  |  | Michelle Lizama
Hawaii - Parks & Rec - Mauna Kea Recreation Permits - Tour Operators |  |  |  | 3: Proposed - INIT | INIT | Self-funded | TBD | TBD | 0% | 0 | Grant Nagata | Reid Sewake | Clayton Honma
DOD - EMS - Hawaii State Trauma Program |  |  |  | 3: Proposed - INIT | INIT | T&M |  |  |  | 24
DOH - EMS - Portal Site |  |  |  | 3: Proposed - INIT | INIT | [6 empty] | Alvin Bronstein
DCCA - PVL - Continuing Education System |  |  |  | 3: Proposed - INIT | INIT | Unknown |  | 2017-04-01 | 0% |  | Charlene Oshiro | Celia Suzuki
DCCA - RICO - Contractor TIP Submission |  |  |  | 3: Proposed - INIT | INIT | Unknown |  |  | 0% |  |  | Daria Loy-Goto
DOH - ADAD - Certified Substance Abuse Counselor Application & Registry System |  |  |  | 3: Proposed - INIT | INIT | T&M |  |  | 0% |  | Angela Bolan | Edward Mersereau
DCCA - RICO - Consolidated Report for Licensees |  |  |  | 3: Proposed - INIT | INIT | Unknown |  |  | 0% |  |  | Daria Loy-Goto
DOH - ADAD - Certified Substance Abuse Counselor Public Search |  |  |  | 3: Proposed - INIT | INIT | T&M |  |  | 0% |  | Angela Bolan | Edward Mersereau
DCCA - RICO - Online Settlement Agreement Payment |  |  |  | 3: Proposed - INIT | INIT | Unknown |  |  | 0% |  |  | Daria Loy-Goto
Kauai - Real Property Tax – Bill Presentment |  |  |  | 3: Proposed - INIT | INIT | Unknown |  |  | 0%
B&F - EUTF - Beneficiary Reimbursement |  |  |  | 3: Proposed - INIT | INIT | Unknown |  |  | 0% |  |  | Raymond Kan | Rodney Shinno
B&F - EUTF - Online Certification |  |  |  | 3: Proposed - INIT | INIT | Unknown |  |  | 0% |  |  | Raymond Kan | Rodney Shinno
CCHNL - DCS - Taxicab Licensing |  |  |  | 3: Proposed - INIT | INIT | Unknown |  |  | 0% |  |  |  | Galen Inouye
JUD - General - Forfeited Bonds |  |  |  | 3: Proposed - INIT | INIT | Unknown |  |  | 0%
CCHNL - DCS - DMV / State ID | 0 | 0 | 0 | 3: Proposed - INIT | INIT | Self-funded |  |  | 0% | 0
DBEDT - Energy - Solar Water Heater Variance | 15706.8 | 0 | 0 | 4: Hold | DEV | Hybrid | 2015-09-14 | 2017-12-15 | 86% | 224 | Dean Masai | Dean Masai | Mark Glick | At Risk
DLNR - DOFAW - State Tree Nursery Seedling Orders |  |  |  | 4: Hold | SOW | Self-funded | 2016-11-07 | 2017-05-05 | 0% |  | Jacob Witcraft | Jay Hatayama
JUD - TVB - Online Driver History & Abstract |  |  |  | 4: Hold | SOW | Self-funded |  |  | 0% |  | Korin Okada | Kevin Thornton | Rodney Maile
CCHNL - DCS - Grants Document Management System | 0 | 0 | 0 | 4: Hold | SOW | T&M |  |  | 0% | 0 | Gabriel Naeole | Barbara Yamashita | Gary Nakata
DOH - OHSM - Hawaii Violent Death Reporting System |  |  |  | 4: Hold | SOW | T&M |  |  | 0% | 0 | Brian Pang | Alvin Onaka
DLNR - Hunter Ed - WP - Instructor Resource Site |  |  |  | 4: Hold | SPEC | T&M | 2016-10-10 | 2017-07-10 | 0% | 11 |  | Andrew Choy | Andrew Choy
AG - Tax & Charities - Charity Registration (Invoicing System) | 0 | 0 | 0 | 4: Hold | SPEC | Hybrid |  |  | 0% | 0 | Kathryn-Jean Kanemori | Kathryn-Jean Kanemore | Hugh Jones | On Track
Kauai - RPT - RPT Redesign Phase I (Multiple Payments) | 0 | 0 | 0 | 5: Completed | LAUNCHED | Self-funded | 2015-03-09 | 2017-04-25 | 100% | 585 | Michelle Lizama | Michelle Lizama | Ken Shimonishi
Judiciary - eBench Warrants Circuit and Family Court Addition | 0 | 0 | 0 | 5: Completed | LAUNCHED | Free | 2016-05-31 | 2017-01-23 | 100% | 111 | Dana Nakasato | Calvin Ching | Kevin Thornton | On Track
Kauai - KPD - eBW Web Service | 0 | 0 | 0 | 5: Completed | LAUNCHED | T&M | 2016-06-13 | 2017-04-28 | 95% | 34 | Stacy Perreira | Rob Gausepohl |  | On Track
Hawaii - HCPD - eBW Web Service | 0 | 0 | 0 | 5: Completed | LAUNCHED | T&M | 2016-06-27 | 2017-04-28 | 95% | 34 | Scott Uehara |  |  | On Track
JUD - Mobile App | 20426.51 | 0 | 0 | 5: Completed | LAUNCHED | T&M | 2016-10-14 | 2017-01-17 | 99% | 258 | Deborah Murray | Deborah Murray | Rod Maile | On Track
Judiciary - Policy and Planning - Appellate Court Judge Evaluation 2017 February | 0 | 0 | 0 | 5: Completed | LAUNCHED | Free | 2016-12-22 | 2017-03-31 | 100% | 10 | Michael Oki |  |  | On Track
ETS - DHRD - 2017 ACA Automation Support | 1860 | 0 | 0 | 5: Completed | LAUNCHED | T&M | 2017-02-23 | 2017-03-31 | 99% | 64.28 | Uyesugi, Dennis | Keane, David |  | On Track
Hawaii - Mass Transit - HeleOn Mobile Bus App (Phase 1) | 0 | 0 | 0 | 6: Canceled | TEST | T&M | 2016-08-08 | 2016-11-14 | 85% | 427 | Tiffany Kai | Tiffany Kai | Mayor Kenoi | Behind
UH - TIM - www.tim.hawaii.edu |  |  |  | 6: Canceled | SOW | T&M | 2016-09-14 | TBD | 0% | 53 | Alan S Okimoto | Thomas Bingham
UH - IFA - Mauna Kea Parking |  |  |  | 6: Canceled | INIT | T&M |  |  |  | 1 | Stewart Hunter
CCHNL - DCS - DMV Site | 0 | 0 | 0 | 6: Canceled | SOW | T&M |  |  | 0% | 0